## BLANK - WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE |  | Project KUSA
PROJECT MANAGER |  | Jimmy Kim & Aiman Lalani
GROUP NAME |  | Asian Byte Architects
DATE |  | 2024-05-01 |  |  |  | Phase One | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Management
1.1 | Define scope | ALL | 2024-02-01 | 2024-02-06 | 4 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 W
1.2 | Define objectives | ALL | 2024-02-01 | 2024-02-06 | 4 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 W
1.3 | Create project tImeline | ALL | 2024-02-01 | 2024-02-06 | 4 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 W
1.4 | Allocate resources | ALL | 2024-02-06 | 2024-02-09 | 4 | bar: WEEK 1 R to WEEK 2 F; WEEK 11 R; WEEK 12 W
1.5 | Develop communications plan | Charlie, Aiman | 2024-02-06 | 2024-02-09 | #NAME? | bar: WEEK 1 R to WEEK 2 F; WEEK 11 R; WEEK 12 W
2 | Research & Planning
2.1 | Conduct stakeholder interview(s) | Jimmy, Aiman, Ryan | 2024-02-14 | 2024-02-16 | 3 | bar: WEEK 1 R to WEEK 2 T; WEEK 3 W to WEEK 3 F; WEEK 11 R; WEEK 12 W
2.2 | Analyze requirements | Willie, Charlie | 2024-02-14 | 2024-02-16 | 3 | bar: WEEK 1 R to WEEK 2 T; WEEK 3 W to WEEK 3 F; WEEK 11 R; WEEK 12 W
2.3 | Research similar club websites | ALL | 2024-02-19 | 2024-02-23 | 5 | bar: WEEK 1 R to WEEK 2 T; WEEK 4 M to WEEK 4 F; WEEK 11 R; WEEK 12 W
2.4 | Define website features and functionalities | ALL | 2024-02-19 | 2024-02-23 | 5 | bar: WEEK 1 R to WEEK 2 T; WEEK 4 M to WEEK 4 F; WEEK 11 R; WEEK 12 W
2.5 | Create wireframes | Ryan | 2024-02-26 | 2024-03-01 | 5 | bar: WEEK 1 R to WEEK 2 T; WEEK 5 M to WEEK 5 F; WEEK 11 R; WEEK 12 W
3 | Design
3.1 | Design visual elements | Ryan, Aiman, Willie | 2024-03-05 | 2024-03-06 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 6 T to WEEK 6 W; WEEK 11 R; WEEK 12 W
3.2 | Create mockups of website pages | Jimmy, Charlie | 2024-03-06 | 2024-03-06 | 1 | bar: WEEK 1 R to WEEK 2 T; WEEK 6 W; WEEK 11 R; WEEK 12 W
3.3 | Conduct testing | ALL | 2024-03-07 | 2024-03-13 | 5 | bar: WEEK 1 R to WEEK 2 T; WEEK 6 R to WEEK 7 W; WEEK 11 R; WEEK 12 W
4 | Development
4.1 | Set up development environment | Jimmy | 2024-03-18 | 2024-03-19 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 8 M to WEEK 8 T; WEEK 11 R; WEEK 12 W
4.2 | Gather feedback from stakeholders | Jimmy, Charlie | 2024-03-20 | 2024-03-20 | 1 | bar: WEEK 1 R to WEEK 2 T; WEEK 8 W; WEEK 11 R; WEEK 12 W
4.3 | Revise design based on feedback | Ryan, Willie | 2024-03-21 | 2024-03-27 | 5 | bar: WEEK 1 R to WEEK 2 T; WEEK 8 R to WEEK 9 W; WEEK 11 R; WEEK 12 W
5 | Content Creation
5.1 | Write website copy | Ryan | 2024-03-27 | 2024-03-27 | 1 | bar: WEEK 1 R to WEEK 2 T; WEEK 9 W; WEEK 11 R; WEEK 12 W
5.2 | Gather multimedia content | Jimmy | 2024-03-28 | 2024-03-28 | 1 | bar: WEEK 1 R to WEEK 2 T; WEEK 9 R; WEEK 11 R; WEEK 12 W
5.3 | Create and organize content for webpages | Charlie, Ryan, Aiman | 2024-03-28 | 2024-03-29 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 9 R to WEEK 9 F; WEEK 11 R; WEEK 12 W
6 | Review & Approval
6.1 | Review website for quality assurance | ALL | 2024-04-01 | 2024-04-01 | 1 | bar: WEEK 1 R to WEEK 2 T; WEEK 10 M; WEEK 11 R; WEEK 12 W
6.2 | Gather feedback from stakeholders | Jimmy, Aiman, Willie | 2024-04-02 | 2024-04-03 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 10 T to WEEK 10 W; WEEK 11 R; WEEK 12 W
6.3 | Make necessary revisions | Charlie, WIllie | 2024-04-03 | 2024-04-05 | 3 | bar: WEEK 1 R to WEEK 2 T; WEEK 10 W to WEEK 10 F; WEEK 11 R; WEEK 12 W
6.4 | Obtain final approval | Jimmy, Ryan | 2024-04-09 | 2024-04-09 | 1 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 T; WEEK 11 R; WEEK 12 W
7 | Deployment
7.1 | Set up hosting environment | ALL | 2024-04-10 | 2024-04-11 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 W to WEEK 11 R; WEEK 12 W
7.2 | Upload website files to hosting server | Ryan, Willie | 2024-04-10 | 2024-04-11 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 W to WEEK 11 R; WEEK 12 W
7.3 | Test website functionality on live server | ALL | 2024-04-11 | 2024-04-12 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R to WEEK 11 F; WEEK 12 W
8 | Training & Documentation
8.1 | Provide training for club members on website management | Jimmy, Charlie, Aiman | 2024-04-16 | 2024-04-17 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 T to WEEK 12 W
8.2 | Create user manuals | Aiman, Ryan, Willie | 2024-04-15 | 2024-04-16 | 2 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 M to WEEK 12 W
9 | Project Closure
9.1 | Conduct project review meeting(s) | ALL | 2024-04-17 | 2024-04-19 | 3 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 W to WEEK 12 F
9.2 | Document lessons learned | ALL | 2024-04-17 | 2024-04-19 | 3 | bar: WEEK 1 R to WEEK 2 T; WEEK 11 R; WEEK 12 W to WEEK 12 F
Formulas:
DURATION = _xludf.DAYS([DUE DATE],[START DATE])